# INTAKEOS MEDICAL

30-DAY LAUNCH PLAN — First Client Onboarded

Start Date: May 16, 2026  |  Target: June 15, 2026  |  Goal: First paying client LIVE

OWNER LEGEND

Phill = Architect/Co-founder (sales, strategy, funding)

Alejandra = Operations Coordinator/Co-founder (execution, verification, admin)

Claude = AI Assistant (content, drafts, checklists, templates — works inside this machine)

Engineer = Contracted developer (milestone-based, paid via Escrow)

"Claude Can Do?" column: YES = Claude produces the deliverable. "Guide only" = Claude gives step-by-step instructions. "No" = requires human action (payment, login, approval).

## WEEK 1 (Days 1-5): FOUNDATION

Priority: Get infrastructure live so the Engineer can start. Domain, email, Escrow, Slack.

| DAY | TASK | OWNER | CLAUDE CAN DO? | STATUS |
| --- | --- | --- | --- | --- |
| 1 | Buy domain arbitrageclaw.com on Cloudflare (~$10.44) | Phill | No — needs card |  |
| 1 | Create Cloudflare account + enable 2FA | Phill | No — needs card |  |
| 1 | Sign up Google Workspace Business Starter | Phill | No — needs card |  |
| 1 | Verify domain in Google Workspace (add TXT record in Cloudflare) | Alejandra | Guide only |  |
| 1 | Add MX record (smtp.google.com) in Cloudflare DNS | Alejandra | Guide only |  |
| 1 | Create operations@arbitrageclaw.com user | Phill | No — admin action |  |
| 1 | Add SPF, DKIM, DMARC records in Cloudflare | Alejandra | Guide only |  |
| 1-2 | Send test email to confirm delivery works | Alejandra | No |  |
| 2 | Sign up Wix Core plan + connect domain (A record + CNAME, gray cloud!) | Alejandra | Guide only |  |
| 2 | Set up OpenPhone business number + voicemail | Phill | No — needs card |  |
| 2 | Create Escrow.com business account + identity verification | Phill | No — needs ID |  |
| 2 | Create Escrow transaction template (4 milestones per Engineer agreement) | Alejandra | YES — I draft the template |  |
| 2-3 | Fund Escrow Milestone 1 ($550 CAD) | Phill | No — needs funds |  |
| 3 | Invite Engineer to Slack + share Escrow milestone details | Alejandra | Draft messages |  |
| 3 | Set up Bitwarden shared vault for credentials | Alejandra | Guide only |  |
| 3 | Create Claude Pro account for Alejandra + IntakeOS Project | Alejandra | Guide only |  |
| 3 | Upload all docs to Claude Project (Engineer Brief, SOUL.md, brand guide) | Alejandra | No |  |
| 3-5 | Engineer starts Milestone 1 (VPS, infrastructure, security) | Engineer | No |  |

## WEEK 2 (Days 6-10): BUILD + VERIFY M1

Priority: Website live, video created, Engineer M1 verified. Sales machine prep begins.

| DAY | TASK | OWNER | CLAUDE CAN DO? | STATUS |
| --- | --- | --- | --- | --- |
| 6 | Write complete website copy — homepage, all vertical pages, CTAs | Claude | YES — full draft |  |
| 6 | Write AI video script (what we do, how, why better, no-risk, compliance) | Claude | YES — full script |  |
| 6-7 | Select Wix template + build homepage with Claude's copy | Alejandra | YES — I pick template + write copy |  |
| 7 | Build vertical pages: /intakeos-medical, /intakeos-legal, /intakeos-dental | Alejandra | YES — I write all content |  |
| 7 | Create Tally.so intake form + connect to Google Sheet | Alejandra | Guide only |  |
| 7-8 | Generate AI demo video using script (HeyGen, Synthesia, or similar) | Phill/Alejandra | YES — I write script, you generate |  |
| 8 | Embed video on homepage + publish website | Alejandra | No — manual in Wix |  |
| 8 | Set up Google Business Profile + submit for verification | Alejandra | YES — I write description |  |
| 8-9 | Configure Wix SEO (titles, meta descriptions, slugs per page) | Alejandra | YES — I write all SEO copy |  |
| 8-10 | Verify Engineer Milestone 1 — run all tests, post evidence in #verification-log | Alejandra | YES — I provide test checklist + commands |  |
| 9-10 | Engineer starts Milestone 2 (API integration, database, agent config) | Engineer | No |  |
| 10 | Set up Wave accounting — connect bank, create expense categories | Alejandra | Guide only |  |
| 10 | Set up Bonsai — service agreement template + invoice template | Alejandra | YES — I draft both templates |  |

## WEEK 3 (Days 11-15): OUTREACH LAUNCH

Priority: Apollo sequences live, first prospects contacted, Engineer M2 verified, M3 starts.

| DAY | TASK | OWNER | CLAUDE CAN DO? | STATUS |
| --- | --- | --- | --- | --- |
| 11 | Set up Apollo.io account | Phill | No — needs card |  |
| 11 | Build Ideal Client Profile (ICP) for Apollo targeting | Claude | YES — full ICP document |  |
| 11-12 | Build prospect list in Apollo: fertility clinics BC + Western US | Claude/Alejandra | YES — I define filters + criteria |  |
| 12 | Build prospect list: cosmetic surgery clinics | Claude/Alejandra | YES — filters + criteria |  |
| 12 | Build prospect list: hair transplant clinics | Claude/Alejandra | YES — filters + criteria |  |
| 12 | Build prospect list: LASIK / ophthalmology clinics | Claude/Alejandra | YES — filters + criteria |  |
| 13 | Write cold email sequence (5-touch, personalized per vertical) | Claude | YES — full sequence |  |
| 13 | Write LinkedIn outreach sequence (connection request + 3 follow-ups) | Claude | YES — full sequence |  |
| 13-14 | Load sequences into Apollo + configure sending schedule | Alejandra | Guide only |  |
| 14 | Launch Apollo sequences — first batch of 50-100 prospects | Alejandra | No — needs approval + send |  |
| 14-15 | Verify Engineer Milestone 2 — run all tests, post evidence | Alejandra | YES — test checklist + commands |  |
| 15 | Engineer starts Milestone 3 (full system integration, voice agent, testing) | Engineer | No |  |
| 15 | Create case study template (for first client success story) | Claude | YES — full template |  |
| 15 | Write 3 LinkedIn posts about AI intake for medical clinics | Claude | YES — full drafts |  |

## WEEK 4 (Days 16-30): CLOSE + ONBOARD

Priority: Convert prospects to signed client, complete Engineer milestones, deploy client system, GO LIVE.

| DAY | TASK | OWNER | CLAUDE CAN DO? | STATUS |
| --- | --- | --- | --- | --- |
| 16-17 | Monitor Apollo responses — reply to interested prospects | Alejandra | YES — I draft replies |  |
| 17 | Send second batch of Apollo outreach (50-100 more prospects) | Alejandra | No — needs send |  |
| 17-18 | Book discovery calls with interested clinics | Phill | No — needs personal touch |  |
| 18 | Create discovery call script + objection handling guide | Claude | YES — full script |  |
| 18 | Create pitch deck (5-7 slides, focus on ROI + risk reversal) | Claude | YES — full deck |  |
| 18-19 | Conduct discovery calls with prospects | Phill | No — needs you live |  |
| 19-20 | Verify Engineer Milestone 3 — full system test | Alejandra | YES — test checklist |  |
| 20 | Engineer starts Milestone 4 (documentation, deployment template, handoff) | Engineer | No |  |
| 20 | Create client onboarding questionnaire | Claude | YES — full questionnaire |  |
| 20 | Create service agreement for first client | Claude | YES — full draft |  |
| 21 | Send proposal + service agreement to top prospect | Phill | YES — I draft proposal |  |
| 21-22 | Follow up with prospects — handle objections, negotiate terms | Phill | YES — I draft responses |  |
| 22-23 | Verify Engineer Milestone 4 — documentation quality test | Alejandra | YES — test checklist |  |
| 23-25 | FIRST CLIENT SIGNS — collect $500 deposit via Wix Payments | Phill/Alejandra | No — needs client action |  |
| 24-25 | Send client onboarding questionnaire | Alejandra | YES — I customize for client |  |
| 25-27 | Receive questionnaire back — write client SOUL.md + AGENTS.md | Phill/Claude | YES — I draft both files |  |
| 27-28 | Deploy client system using Deployment Template | Alejandra/Engineer | YES — I guide deployment |  |
| 28-29 | Run end-to-end test with client (form → voice agent → booking → reminders) | Alejandra | YES — I write test script |  |
| 30 | CLIENT GOES LIVE — system active, intake running 24/7 | All | Celebration time! |  |

## TASKS CLAUDE HANDLES INDEPENDENTLY

These are deliverables Claude produces in full. You review, approve, and deploy.

Content & Copy

- Complete website copy — homepage, vertical pages, CTAs, about page

- AI video script — what you do, how, why you're better, compliance, no-risk pitch

- SEO meta descriptions, page titles, and slugs for every page

- Google Business Profile description (150 words)

- LinkedIn posts (3+ posts about AI intake for medical clinics)

- Blog articles for SEO and thought leadership

Sales & Outreach

- Ideal Client Profile (ICP) document with targeting criteria

- Apollo.io prospect list filters and search criteria per vertical

- Cold email sequence (5-touch, personalized per vertical)

- LinkedIn outreach sequence (connection request + 3 follow-ups)

- Reply templates for interested prospects

- Discovery call script + objection handling guide

- Pitch deck (5-7 slides focused on ROI + risk reversal)

- Proposal template for first client

Operations & Legal

- Service agreement template (Bonsai-ready)

- Invoice template (retainer + success fee lines)

- Client onboarding questionnaire

- Escrow milestone transaction template (4 milestones)

- Case study template (for first client success story)

Engineer Verification

- Milestone 1 verification checklist with exact commands to run

- Milestone 2 verification checklist with exact commands to run

- Milestone 3 verification checklist with exact commands to run

- Milestone 4 documentation quality verification checklist

- Client SOUL.md and AGENTS.md drafts (per client vertical)

## CRITICAL PATH — WHAT BLOCKS EVERYTHING

If any of these slip, the 30-day target is at risk:

- Day 1-2: Escrow must be funded so Engineer can start. No funding = no product = no client.

- Day 8-10: Engineer M1 must pass verification. If it fails, M2 can't start and timeline shifts.

- Day 14: Apollo outreach must launch. Every day of delay = fewer prospects in the pipeline.

- Day 18-19: Discovery calls must happen. No calls = no client by Day 30.

- Day 22-23: Engineer M4 must be complete. Client can't go live without the deployment template.

ESTIMATED PHASE 1 BUDGET

| ITEM | COST |
| --- | --- |
| Domain (Cloudflare, 1 year) | ~$10 USD |
| Google Workspace (1 user, monthly) | $8.40 USD/month |
| Wix Core plan (monthly) | ~$17 USD/month |
| OpenPhone (1 number) | $15 USD/month |
| Claude Pro (Alejandra's account) | $20 USD/month |
| Apollo.io (Basic plan) | $49 USD/month |
| AI Video Tool (HeyGen/Synthesia, 1 month) | ~$29-59 USD |
| Engineer — All 4 Milestones (via Escrow) | $2,100 CAD (~$1,550 USD) |
| Escrow.com fees (~3.25%) | ~$68 CAD |
| TOTAL PHASE 1 (approximate) | ~$1,850-$1,950 USD |

Generated by Claude (Control Tower) — May 16, 2026

This is a living document. Update STATUS column as tasks are completed.